## Dashboard
Go Technical Learning Roadmap
Learning Objective | Build practical Go backend and systems-development capability from beginner to production level.
Recommended Pace | 8–10 hours/week
Roadmap Duration | 24 weeks / approximately 6 months
Primary Outcome | Build and deploy production-style Go services, understand concurrency/memory/performance, testing, security and cloud-native patterns.
Suggested Approach | 30% theory + 60% coding + 10% review/documentation
Background Alignment | Use existing .NET/backend experience to map concepts, but learn the language idioms rather than writing .NET-style code.
Recommended Learning Sequence
1. Language fundamentals
2. Idiomatic coding
3. Standard library
4. Concurrency / async
5. Web & APIs
6. Databases & messaging
7. Testing & observability
8. Security
9. Containers & cloud
10. Capstone

## Learning Roadmap
Phase | Duration | Level | Technical Area | Topics to Learn | Hands-on Practice | Milestone / Outcome | Status | Target Date | Notes
1. Foundation | Weeks 1–2 | Beginner | Go setup & syntax | Install Go; modules; package/main; variables; constants; types; operators; if/for/switch; functions; multiple returns; errors; formatting | Build CLI calculator, temperature converter and file-based TODO app | Can create, run, format and debug small Go programs | Not Started
2. Go Idioms | Weeks 3–4 | Beginner | Core language | Arrays/slices; maps; structs; methods; pointers; interfaces; embedding; type assertions; zero values; defer; panic/recover | Implement an in-memory inventory and order domain model | Understand idiomatic Go data modeling and interfaces | Not Started
3. Standard Library | Weeks 5–6 | Beginner–Intermediate | Files, HTTP, JSON | os; io; bufio; strings; time; encoding/json; net/http; context; log/slog; regexp | Create JSON file processor and a REST client | Comfortable using standard library before reaching for frameworks | Not Started
4. Error Handling & Design | Weeks 7–8 | Intermediate | Production coding patterns | Error wrapping; sentinel/custom errors; validation; dependency injection with interfaces; package design; configuration; environment variables | Refactor an API into clean packages with explicit dependencies | Can structure maintainable Go services | Not Started
5. Concurrency | Weeks 9–10 | Intermediate | Goroutines & channels | Goroutines; channels; buffered/unbuffered; select; sync.Mutex; RWMutex; WaitGroup; atomic; worker pools; race detector | Build concurrent job processor and bounded worker pool | Understand safe concurrent execution and back-pressure | Not Started
6. Web API | Weeks 11–12 | Intermediate | HTTP services | HTTP server/client; middleware; routing; context cancellation; request validation; JSON; graceful shutdown; timeouts | Build production-style Order/Customer REST API | API with validation, structured errors and graceful shutdown | Not Started
7. Database & Messaging | Weeks 13–14 | Intermediate | Persistence & integration | database/sql; PostgreSQL/SQL Server; transactions; connection pools; migrations; RabbitMQ/Kafka concepts; retries/idempotency | Add DB persistence and async event publishing to API | Reliable data and integration patterns | Not Started
8. Testing & Quality | Weeks 15–16 | Intermediate | Testing | testing package; table-driven tests; benchmarks; httptest; mocks/fakes; integration tests; fuzz testing; race detection; profiling basics | Reach meaningful test coverage and add benchmarks | Repeatable automated quality gates | Not Started
9. Observability & Security | Weeks 17–18 | Intermediate–Advanced | Production readiness | Structured logging; metrics; traces/OpenTelemetry concepts; secrets; TLS; auth/JWT concepts; input validation; OWASP API risks | Instrument service and secure endpoints | Service has useful logs/metrics/traces and security controls | Not Started
10. Containers & Cloud | Weeks 19–20 | Advanced | Deployment | Multi-stage Docker; health checks; config; Kubernetes basics; probes; resource limits; CI/CD; cloud deployment concepts | Containerize and deploy API with CI pipeline | Repeatable build/deploy process | Not Started
11. Performance & Systems | Weeks 21–22 | Advanced | Profiling & optimization | pprof; CPU/memory profiling; allocations; GC concepts; benchmarking; connection pooling; load testing; caching | Profile API under load and optimize bottlenecks | Evidence-based performance optimization | Not Started
12. Capstone | Weeks 23–24 | Advanced | Enterprise Go | Architecture; domain boundaries; API; DB; messaging; concurrency; tests; observability; security; deployment | Build Order Processing Platform with REST + PostgreSQL + RabbitMQ + background workers | Portfolio-ready enterprise Go project with architecture documentation | Not Started

## Skill Tracker
Skill Category | Skill | Priority | Target Level | Status | Practice Evidence | Notes
Language | Syntax & control flow | High | Strong | Not Started
Language | Slices, maps, structs, pointers | High | Strong | Not Started
Language | Interfaces & idiomatic design | High | Strong | Not Started
Language | Error handling | High | Strong | Not Started
Standard Library | HTTP, JSON, context, files | High | Strong | Not Started
Concurrency | Goroutines & channels | High | Strong | Not Started
Concurrency | Synchronization & race detection | High | Strong | Not Started
Backend | REST API development | High | Strong | Not Started
Data | database/sql & transactions | High | Working | Not Started
Testing | Unit/integration/benchmark/fuzz | High | Strong | Not Started
Production | Logging, metrics, tracing | High | Working | Not Started
DevOps | Docker, Kubernetes, CI/CD | Medium | Working | Not Started
Performance | Profiling, allocations, benchmarking | Medium | Working | Not Started
Security | API security, TLS, secrets | Medium | Working | Not Started

## Projects
Project | Difficulty | Skills Covered | Expected Deliverables | Suggested Timeline | Status
CLI Productivity Toolkit | Beginner | Packages, structs, interfaces, file I/O, JSON, errors | CLI commands, config file, tests, README | 2 weeks | Not Started
Concurrent Job Processor | Intermediate | Goroutines, channels, worker pools, context, retries | Worker service, queue, cancellation, metrics, tests | 2–3 weeks | Not Started
Enterprise Order API | Intermediate | HTTP, JSON, DB, transactions, validation, logging, testing | REST API, PostgreSQL, OpenAPI, integration tests | 3–4 weeks | Not Started
Order Event Processor | Advanced | RabbitMQ/Kafka concepts, idempotency, concurrency, observability | Consumer, retry/DLQ design, idempotency, tracing | 3 weeks | Not Started
Go Production Capstone | Advanced | All roadmap areas | Architecture diagram, API, DB, messaging, Docker, CI/CD, tests, monitoring | 4–6 weeks | Not Started

## Weekly Plan
Week | Focus | Theory / Reading | Coding Practice | Deliverable | Hours / Week | Status
1 | Setup & Go mental model | Go toolchain, modules, packages | CLI Hello + calculator | Git repo + notes | 8 | Not Started
2 | Control flow & functions | Types, functions, errors | File-based TODO CLI | Working CLI | 8 | Not Started
3 | Slices, maps, structs | Data modeling | Inventory service in memory | Domain model | 8 | Not Started
4 | Pointers & interfaces | Methods, interfaces, embedding | Refactor inventory using interfaces | Idiomatic design | 8 | Not Started
5 | Standard library | os/io/json/time | JSON file processor | Reusable utility package | 8 | Not Started
6 | HTTP basics | net/http, context | REST client + simple server | HTTP service | 8 | Not Started
7 | Packages & errors | Error wrapping, config | Clean package structure | Service skeleton | 8 | Not Started
8 | Testing | testing, table tests | Test previous service | Automated tests | 8 | Not Started
9 | Goroutines | Concurrency model | Parallel file processor | Concurrent program | 9 | Not Started
10 | Channels & workers | select, WaitGroup, worker pool | Job processor | Bounded worker pool | 9 | Not Started
11 | REST API | Handlers, middleware, validation | Order API endpoints | API v1 | 9 | Not Started
12 | API quality | Timeouts, graceful shutdown | Error model + middleware | Production API skeleton | 9 | Not Started
13 | Database | database/sql, PostgreSQL | Persistence layer | DB-backed API | 9 | Not Started
14 | Transactions & integration | Transactions, retries, messaging | Order event publishing | Reliable integration | 9 | Not Started
15 | Testing depth | httptest, integration tests | API test suite | Quality gate | 8 | Not Started
16 | Benchmarks & fuzz | Benchmark/fuzz/race | Benchmark hot path | Quality/performance baseline | 8 | Not Started
17 | Observability | Structured logs, metrics | Instrument API | Observable service | 8 | Not Started
18 | Security | JWT concepts, TLS, validation | Secure API endpoints | Security baseline | 8 | Not Started
19 | Docker | Multi-stage build | Containerize service | Docker image | 8 | Not Started
20 | Kubernetes & CI/CD | Probes, manifests, pipeline | Deploy to local K8s | Deployment pipeline | 9 | Not Started
21 | Profiling | pprof, allocations | Load-test API | Profile report | 9 | Not Started
22 | Optimization | DB/API/cache tuning | Fix measured bottlenecks | Before/after metrics | 9 | Not Started
23 | Capstone | Architecture review | Build order platform | Release candidate | 10 | Not Started
24 | Capstone | Documentation + hardening | Demo, tests, deployment | Portfolio release | 10 | Not Started